## Sprint1
Sprint1
| Start Date | Duration
GitHub repository | 2020-02-03 | 1
Excel parser | 2020-02-03 | 5
Board object | 2020-02-04 | 5
PropertyCard objects | 2020-02-04 | 5
Dice object | 2020-02-04 | 5
Player objects | 2020-02-04 | 5
Bank object | 2020-02-04 | 5
Testing | 2020-02-09 | 1

## Sprint2
Sprint 2
| Start Date | Duration
Rent feature | 2020-02-10 | 1
Update game objects | 2020-02-10 | 1
Basic GUI | 2020-02-10 | 7
Text-based game | 2020-02-11 | 1
Possible player actions | 2020-02-12 | 5
Player tokens | 2020-02-13 | 4

## Sprint3
Sprint 3
| Start Date | Duration
Card parser | 2020-02-17 | 1
Token images | 2020-02-17 | 5
Button methods | 2020-02-17 | 7
Card action methods | 2020-02-18 | 3
Property structure | 2020-02-19 | 2
Dice revision | 2020-02-20 | 1

## Sprint4
Sprint 3
| Start Date | Duration
redesign project | 2020-02-24 | 2
fix old test classes | 2020-02-26 | 1
created packages | 2020-02-26 | 1
GameController class | 2020-02-27 | 2
fix Bank class | 2020-02-27 | 4
fix Player class | 2020-02-27 | 4
fix Dice class | 2020-02-27 | 4
fix Board class | 2020-02-27 | 4