## Sprint1
Sprint1
| Start Date | Duration
GitHub repository | 2020-02-03 | 1
Excel parser | 2020-02-03 | 5
Board object | 2020-02-04 | 5
PropertyCard objects | 2020-02-04 | 5
Dice object | 2020-02-04 | 5
Player objects | 2020-02-04 | 5
Bank object | 2020-02-04 | 5
Testing | 2020-02-09 | 1

## Sprint2
Sprint 2
| Start Date | Duration
Rent feature | 2020-02-10 | 1
Update game objects | 2020-02-10 | 1
Basic GUI | 2020-02-10 | 7
Text-based game | 2020-02-11 | 1
Possible player actions | 2020-02-12 | 5
Player tokens | 2020-02-13 | 4

## Sprint3
Sprint 3
| Start Date | Duration
Card parser | 2020-02-17 | 1
Token images | 2020-02-17 | 5
Button methods | 2020-02-17 | 7
Card action methods | 2020-02-18 | 3
Property structure | 2020-02-19 | 2
Dice revision | 2020-02-20 | 1

## Sprint4
Sprint 4
| Start Date | Duration
redesign project | 2020-02-24 | 2
fix old test classes | 2020-02-26 | 1
create packages | 2020-02-26 | 1
GameController class | 2020-02-27 | 2
fix Bank class | 2020-02-27 | 4
fix Player class | 2020-02-27 | 4
fix Dice class | 2020-02-27 | 4
fix Board class | 2020-02-27 | 4

## Sprint5
Sprint 5
| Start Date | Duration
Mortgaging properties | 2020-03-02 | 2
Auctionning mechanic | 2020-03-02 | 2
BoardPieces onto GUI | 2020-03-02 | 3
Houses and hotels | 2020-03-02 | 5
Log system | 2020-03-04 | 5
Start screen in GUI | 2020-03-05 | 4

## Sprint6
Sprint 6
| Start Date | Duration
Trading system | 2020-03-26 | 6
GUI Scene builder | 2020-03-27 | 5
unMortgage method | 2020-03-30 | 3
Auction data structure | 2020-04-01 | 7
Max houses on property | 2020-04-02 | 1
Double rent | 2020-04-02 | 2
Show log in GUI | 2020-04-02 | 4
houseChecks in buyHouse | 2020-04-03 | 1
No buying until after 1 loop | 2020-04-03 | 3

## Sprint7
Sprint 7
| Start Date | Duration
auction check | 2020-04-06 | 2
update GUI | 2020-04-06 | 7
redo auction if check fails | 2020-04-08 | 2
create basic AI to play game | 2020-04-08 | 5
sellProperty unmortgage issue | 2020-04-09 | 1
list of upgradable properties | 2020-04-10 | 1

## Sprint8
Sprint 8
| Start Date | Duration
Stations/Utilities cannot be bought in first loop | 2020-04-13 | 1
Fix rolling doubles issue | 2020-04-13 | 2
Animate tokens as gifs in GUI | 2020-04-13 | 5
In auction, if all bids 0, cancel auction | 2020-04-14 | 4
Fix doubles jail issue | 2020-04-15 | 3
Fix landing on Go issue | 2020-04-18 | 2

## Sprint9
Sprint 9
| Start Date | Duration
If property owner in jail, no rent | 2020-05-01 | 1
Implement getOutOfJailFree cards | 2020-05-01 | 2
Method to check if player can afford houses | 2020-05-01 | 5
Bugs relating to last sprint | 2020-05-01 | 5
Writing documentation | 2020-05-01 | 7
Add £200 when player's loopCount increases | 2020-05-02 | 2
If jailed player pays to leave, money to FreeParking | 2020-05-03 | 2

## Sprint10
Sprint 9
| Start Date | Duration
Complete documentation | 2020-05-08 | 7
Add winning conditions for both versions | 2020-05-09 | 3
Finish timed version of game | 2020-05-10 | 4
Make PropertyTycoon logo | 2020-05-12 | 1
Create team logo | 2020-05-12 | 1
Record video of game being played | 2020-05-14 | 1
Make public the GitHub repository | 2020-05-14 | 1